## Sheet1
Kay Creek Hut restoration
Projects | Priority | Detail of works | Materials | Quantity | Skilled/unskilled | Approximate duration | Tools | Costs
Water/weather proof hut | 1 | Remove rock, soil and vegetation around hut. | Drill bits for dyna drill | 1 X 180mm | U | 2 pax 0.5 - 1.0 day | Picks, grubber, trench spade, bars
|  | Create trenches to take water away from hut |  | 1 x 200mm | U |  | Dyna drill and bits (up to 200mm)
Generator 2kva, power leads, fuel
safety equipment (gloves, goggles, ear muffs)
Remove existing fittings and floor | 2 | Remove existing bunks, large stones on floor |  |  | U | 2/3 pax 0.25 day | Reciprocating saw, jimmy bar, hack saw, hammer, fencing pliers
|  | bench and other internal fittings. Salvage |  |  |  |  | Leather gloves
|  | any sound timber. |  |  |  |  | Chain saw, fuel (to be used by Frank Pepers qualified saw instructor)
Reframing and base work | 3 | Remove & replace rotten base logs and where necessary | Ready mix concrete 25kg per | 4 bags | S (U assist) | 2 pax 1.0 day | Chain saw, petrol, safety gear
|  | studs. Rebuild door surround to fit jam. Concrete in door studs. | Fixings. Details at end |  |  |  | Bars, recip saw, sledge hammer, spirit level
|  | Two cut down waratahs per other major studs and secure | Waratahs @ 1500mm | 10 |  |  | Wheel barrow to mix concrete
|  | Studs and base plates from local saplings | redrilled |  |  |  | Buckets for water
|  |  | Angle grinder discs | 2 |  |  | Angle grinder
Level and finish floor | 4 | Source and shift gravel from Kay Creek |  |  | U | 4 pax 0.25 day | Shovels (small and large head)
| 5 | Relevel floor with stones and gravel finish |  |  | U (S assist) | 2-3 pax 0.3 day | Wheel barrow, buckets, rake, ear muffs, leather gloves
Reposition truss/cross members | 6 | Reposition truss/cross members above head height. | Some fixings as per end |  | S (U assist) | 2 pax 0.25 day | Hand saw, jimmy bar, recip saw
|  | Stabilise hut frame with existing/new saplings |  |  | S (U assist) |  | Cordless driver plus drill bits and driving bits
Fit new bunks | 7 | Assemble precut bunks. | Ready mix concrete 25 kg per | 8 bags | S (U assist) | 2-3 pax 0.5 day | Bar, shovel, level, hand saw, tape measures
|  | Position and cement corner posts in floor. Fix bunks in position | 150mm x 50mm H3 timber @ 2.4m (min) dressed | 8
|  |  | 100mm x 25mm H3 timber @ various lengths ok | 60m in total
|  |  | Galv 10mm bolt, nut and washer | 40
Fit new door | 8 | Hang new door | Door and hinges provided |  | S (U assist) | 1-2 pax 0.25 day | level, driver, hand saw
Fixings as per end
|  |  | wooden spacers | various pieces gauged timber
no 8 wire for simple latch in/out
|  |  | large staples | 12
Fit new (2nd hand) windows | 9 | Place two separate, 6 pane windows in W and E walls for light | 2 x windows up to 700mm square | 2 | S (U assist) | 2 pax 0.5 day | Drill, hack saw, tin snips, driver, hammer, level,
|  | Build window surrounds, facings and flashings | 100mm x 25mm rough sawn oregon | 8 metres
|  | Dry beech to make window surrounds | Silicon cartridge apt rust/grey colours | 4 cartridges
fixings as per end
Fit new (2nd hand) steel bench | 10 | Fix and support new bench in hut using beech timber | Stainless steel bench 2m provided |  | S (U assist) | 2 pax 0.15 day | Hand saw. Level. Driver and bits
Fixings as per end
Chimney rebuild | 11 | Remove old chimney. Salvage iron. |  |  | U | 1 pax 0.15 day | Tin snips, hack saw, leather gloves
|  | Install new fire place lintel. Shape new chimney and install | Corrugated iron sheets @ 2.4 (standard gray) | 6 | S (U assist) | 2 pax 0.5 day | Pop riveter and rivets
|  |  | Pop rivets | see rivets below water tank |  |  | Sledge hammer
|  |  | Short bolts and nuts |  |  |  | Fencing pliers, regular pliers
|  |  | Waratahs for chimney support | 4 x 1.8m
|  |  | Maleable wire (2 gauges) | 1 x coil no 8 wire (min 30m) | 1
|  |  |  | 1 x coil lighter gauge (min 30m) | 1
|  |  | Metal lintel for fire place | 75mm x 1.2m right angle bar
Replace lead nails and lead cap roof seal | 12 | Remove old lead head nails and ridge cap lead seal. Replace | Lead sheet replacement roof cap seal | 5m long on both sides | U (S assist) | 2 pax 0.5 day
plus building paper and netting |  | orginal building paper (add wire net). Replace seal and renail | Building paper | 20 sq.m (hut is 4.5 x 3.1)
|  |  | Chicken netting | 20 sq.m (hut is 4.5 x 3.1)
|  |  | Small staples to fix netting to perlins | approx 100
Outdoor wood shed | 13 | Set beech saplings in ground. Cross members and iron | Corrugated iron sheets (aged) | 6 sheets @ 2m+ | U (S assist) | 2 pax 0.3 day | Bar, trench shovel, earth rammer, level, driver and bit
|  | walls and roof | Roofing fixers as per end
New long drop | 14 | Dig hole in suitable location (max depth 1.5m) |  |  | U | 1-2 pax 0.3 day | Bars, trench shovel,
|  | Assemble pre made frames, door, cladding and toilet seat | 150mm x 150mm H4 treated posts @ 2.7m | 2 | S (U assist) | 2 pax 0.5 day
|  |  | Corrugated iron sheets @ 2.4m | 7
|  |  | 100mm x 50mm H3 treated timber | 60m
|  |  | 75mm x 50mm H3 treated timber | 10m
|  |  | 150mm x 25mm H3 treated timber | 15m
|  |  | 2400 x 1200 ply wood sheets treated | 2
|  |  | 100mm galv jolt nails | 5kg
|  |  | no 8 wire latches | noted above
|  |  | staples | noted above
fixings for frame and toilet see below
Create new tent site beside hut | 15 | Remove large boulders and create level area for 4 person tent |  |  | U | 1-2 pax 0.25 day | bars, shovel
New water tank | 16 | Build tank stand | Approx 400 litre plastic water tank | 1 | S (U assist) | 1-2 pax 0.5 day | Driver, drill set and drive bits, hand saw
|  | Mount tank | Aged metal gutter (up to 4.5m long) with | 1 x up to 4.5m | S (U assist) | 1 pax 0.1 day
down pipe fitting R end
|  | Fix gutter, down pipe, overflow and tap | Strap to mount gutter to roofing iron |  | S (U assist) | 1-2 pax 0.2 day
|  |  | Rivets to fix gutter to strap/roof | 5mm diameter x 200
|  |  | Down pipe to tank and overflow | 5m x 90mm
|  |  | Pipe bends for in/out pipe | 4 x 45 degree
4 x 90 degree
|  |  | Short screws to fix pipe and bends. Sq head | 20 x 10mm
|  |  | Bags 25kg concrete for corner posts | 8 bags
|  |  | 100mm X 100mm x 1.2m H4 posts | 4
|  |  | 100mm X 50mm H4 timber | 20m
|  |  | 10mm x 135mm galv bolt/nut/washer | 20
Fasteners for various jobs above
Internal
|  |  | 50mm square headed drivers | 100
|  |  | 65mm square headed drivers | 100
|  |  | 75mm square headed drivers | 200
|  |  | 100mm square headed drivers | 200
External
|  |  | Galv 120mm square headed screws | 50
Ga |  |  | Galv 100mm jolt nails | 5 kg
|  |  | Galv 150mm jolt nails | 2.5kg
|  |  | Galv 65mm roof screws with dull (rust) head | 500
Spare cladding (in addition to requested above)
|  |  | Rusty corrugate sheets up to 2.4 length | 4
|  |  | Aged flat galv sheet various sizes useful | 6
Bunks and Long drop - please provide or specify
fixings in order to assemble these.
Total estimated person hours |  | Total of breakdown above 1 - 16 |  |  |  | 17-18 person days min
Total person hours available |  | 6 days (28th March - 3rd April) x 6 - 8 people |  |  |  | 36 - 42 person days | Before weather, delays etc
Staff 2 skilled, 1 semi-skilled, 3-5 unskilled